## Functional
Project Name: | Art Echo
Superviser Name: | Sir Muhammad Naveed
Deliverable: | Project Status
ID | Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | Artist can signup | High | 100% | N/A | Osama, Hiba
2 | Artist can login/logout | High | 100% | N/A | Osama, Hiba
3 | Admin can login/logout | High | 100% | N/A | Osama, Hiba
4 | User can Signup | High | 100% | N/A | Osama, Hiba
5 | User can login/logout | High | 100% | N/A | Osama, Hiba
6 | Artist can make posts | High | 100% | N/A | Hiba, Abdullah
7 | Artist can upload items for sale | High | 80% | 8 | Hiba, Abdullah
8 | Artist upload items to VR Gallery | High | 90% | 7 | Abdullah, Osama
9 | Artist can participate in Events | Medium | 70% | 9 | Osama
10 | Artist can create Events | Medium | 70% | 9 | Osama, Hiba
11 | Artist can like/comment on posts | Medium | 100% | N/A | Osama, Hiba
12 | User can like/comment on posts | Medium | 100% | N/A | Osama, Hiba
13 | Artist can view other Artists' profile | Medium | 100% | N/A | Abdullah, Osama
14 | User can view other Artists' profile | Medium | 100% | N/A | Abdullah, Osama
15 | Artist can participate in Events | Medium | 70% | 9 | Osama
16 | Artist can add other Artists as friends | Medium | 100% | N/A | Abdullah, Osama
17 | User can follow Artists | Medium | 90% | 8 | Abdullah
18 | Artist can update username/password | Low | 80% | 8 | Abdullah
19 | User can update username/password | Low | 80% | 8 | Abdullah
20 | Admin can delete Users/artists | Medium | 70% | 7 | Osama, Hiba
21 | Admin can delete posts | Medium | 70% | 7 | Osama, Hiba
22 | Admin verifies Artist account | High | 60% | 9 | Abdullah, Osama
23 | Admin approves artworks for posting to VR Gallery | High | 100% | N/A | Hiba, Abdullah
24 | Admin can start/end events | Medium | 70% | 9 | Osama

## Non-Functional
Project Name: | Art Echo
Superviser Name: | Sir Muhammad Naveed
Deliverable: | Project Status
ID | Non-Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | Users will be able to learn about main functionalities in 2 to 4 tries. | Medium | 100% | N/A | Osama, Hiba
2 | The app must be able to support at least 50 users at a time. | High | 30% | N/A | Osama, Hiba
3 | The web application response time should respond in 2-3 seconds in desktop and mobile browsers. | Medium | 30% | N/A | Osama, Hiba
4 | The language for web application will be English. | Low | 100% | N/A | Hiba, Abdullah
5 | The user’s data is end-to-end encrypted by TLS/SSL protocols. | High | 0% | N/A | Hiba, Abdullah
6 | The web application must not fail in 98 percent of the cases. | High | 70% | N/A | Abdullah, Osama
7 | The MTTR should be 20 minutes after the detection of a system failure. | Medium | 0% | N/A | Osama
8 | It must be accessible 24/7. | Medium | 10% | N/A | Osama, Hiba
9 | The application should be scalable to support 500 users at a time with the optimal performance. | Low | 0% | N/A | Abdullah
10 | The web application can run on all devices which support modern browsers: Chrome, Edge, Firefox and Safari. | High | 40% | N/A | Abdullah
11 | The system should be able to alert customers in real-time with a maximum 5-second latency between the incident and message reception. | High | 100% | N/A | Osama, Hiba
12 | The system should be able to store at least 100 works of art with photographs, descriptions, and other information | High | 80% | N/A | Osama, Hiba
13 | The system should be able to handle user uploads of pictures and videos for postings with a file size restriction of 10 MB | High | 100% | N/A | Abdullah, Osama

## Instructions
Instructions For Completing This Document
Complete the Project Name and Superviser Name
ID: A unique ID number used to identify the requirement
Functional Requirement: This column should be populated with a description of the functional requirement. | Non-Functional Requirement: This column should be populated with a description of the non-functional requirement.
Status: This column should be populated with the current status of the functional requirement.
Deadline: This column should be populated for the requirements whose status is incomplete.
Resource: Team member who completed/will complete the requirement implmentation.